## Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2019
Province, City or Municipality: GUINDULMAN, BOHOL
Program or Project | Location | Total Cost (Balance Beg. 1/1/2019) | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development:
2012- Purchased of BCCTV Camera |  | 50000 |  |  |  | 0
2016- Rehab. Barangay Health Station-Tabunoc |  | 200000 |  |  |  | 0
2016- Rehab. & Imprmnt of Bulawan Day Care Center |  | 53572.57 |  |  |  | 0
2017- SOCIAL DEVELOPMENT- Completion of Covered Court at Barangay Bayong |  | 30686.5 |  |  |  | 0
2017- SOCIAL DEVELOPMENT- Completion of Covered Court at Barangay Guinacot |  | 10093.5 |  |  |  | 0
2017- SOCIAL DEVELOPMENT- Improvement of Mun. Gymnasium (Equipment & Acoustic Sounds) |  | 9100.8 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Multi-Purpose Covered Court/Hall at Central,Casbu |  | 557202 |  |  |  | 444200
2018- SOCIAL DEVELOPMENT- Contruction of Multi-Purpose Hall at the 2nd Floor of Municipal Fishport Bldng. |  | 1000000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Improvement & Renovation of Old PNP Bldng. For conversation into a Multi-Purpose Hall |  | 500000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Multi-Purpose Covered Court/Hall (Phase I) at Sitio Fatima,Cat. Sur |  | 367932 |  |  |  | 363500
2018- SOCIAL DEVELOPMENT- Construction of Multi-Purpose Covered Court/Hall (Phase I) at Central Guio-ang |  | 365832 |  |  |  | 342000
2018- SOCIAL DEVELOPMENT- Construction of Reservoir & Pipelines at Guinacot Nat'l. High School |  | 35353 |  |  |  | 19725
2018- SOCIAL DEVELOPMENT- Installation of Streetlighting from Purok 1, Purok 2, Bato-Bulawan Boundary and Bato-Casbu Boundary |  | 8734 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Partial Construction of Cansiwang Barangay Multi-Purpose Hall |  | 42785.5 |  |  |  | 41880.87
2018- SOCIAL DEVELOPMENT- Installation of Casbu Streetlighting |  | 60769 |  |  |  | 39000
2018- SOCIAL DEVELOPMENT- Construction of Multi-Purpose Center (Storage Room and Garage) for Pansul United Farmers' Association (PUFA)- Cabantian (SB Resol No. 2018-02-21) |  | 30000 |  |  |  | 29767
2018- SOCIAL DEVELOPMENT- Construction of Reservoir and Distribution Pipe @ Sitio Bantig, Mayuga |  | 12351 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Water Reservoir @ Catungawan Sur |  | 170000 |  |  |  | 147889
2018- SOCIAL DEVELOPMENT- Installation of Streetlight @ Bulawan |  | 6750 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Installation of Streetlight @ Tabunok- Guinto-owan |  | 3567 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Completion of Eskaya Multi-Purpose Building (Biabas) |  | 12116.45 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Installation of Distribution Transformer at PNP Guindulman |  | 170000 |  |  |  | 155440.72
2018- SOCIAL DEVELOPMENT- Mayuga Multi-Purpose Building Improvement |  | 200000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Mayuga- Footbridge and Pathway from Chapel to Sitio Camagong I |  | 100000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Mayuga- Footbridge and Pathway from Sitio Camagong II to Chapel |  | 100000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Biabas- Initial Construction of Senior Citizens' Building |  | 150000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT - Completion of Tribal House (Eskaya Tribe) at Barangay Biabas |  | 100000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Waterworks at Fatima, Cabantian |  | 100000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Completion of Barangay Multi-Purpose Hall, Cansiwang |  | 450000 |  |  |  | 196224
2019 - SOCIAL DEVELOPMENT -Constructon of School Stage at Barangay Casbu |  | 200000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Construction of Reservoir-Waterworks Project-Sitio Ilaud, Casbu (Drilling, etc.) |  | 400000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Installation of Road Railing at Sitio Mabago to Poo, Catungawan Sur |  | 100000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of School Stage at Catungawan National High School |  | 100000 |  |  |  | 99945
2019 - SOCIAL DEVELOPMENT -Additional Funding for Multi-Pupose Covered Court at Barangay Casbu |  | 850000 |  |  |  | 646630
2019 - SOCIAL DEVELOPMENT -Improvement of Oval (Track & Field) at Central Elementary School |  | 500000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Additional Funding for Multi-Purpose Covered Court of Barangay Catungawan Sur |  | 1000000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Multi-Purpose Building (Senior Citizen)- Barangay Guio-ang |  | 100000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Tubod Spring at Barangay Guio-ang |  | 300000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Additional Funding for Multi-Purpose Covered Court of Barangay Guio-ang |  | 800000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Mayuga Waterworks System, Barangay Mayuga |  | 300000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Installation of Street Lightings along FCB, Bonita & Liao Street, Barangay Sawang |  | 250000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Installation of Barangay Street Lighting at Barangay Bulawan |  | 200000 |  |  |  | 147265
2019 - SOCIAL DEVELOPMENT -Construction of Public Comfort Room at Barangay Tabajan |  | 250000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Senior Citizen Meeting Hall- Barangay Tabajan |  | 250000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Additional Funding for the Completion of Covered Court at Barangay Trinidad |  | 500000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Construction of Bamboo Houses for the Improvement of Marine Sanctuary at Barangay Basdio |  | 500000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Site Development of LGU Lot in Guio-ang |  | 2000000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Additional Construction of Grandstand at Central Elementary School |  | 500000 |  |  |  | 357008
2019 - SOCIAL DEVELOPMENT -Rehabilitation of Guindulman Gymnasium (Major Repair of Roofing) |  | 500000 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
SUB-TOTAL |  | 14496845.32 |  |  |  | 3030474.59
Economic Development:
2016- Concreting of Public Market Sorrounding |  | 26166.2 |  |  |  | 0
2017- ECONOMIC DEVELOPMENT- Improvement of Slaughterhouse, Barangay Canhaway |  | 500000 |  |  |  | 271890
2017- ECONOMIC DEVELOPMENT- Improvement of Waterworks, Barangay Tabunoc |  | 200000 |  |  |  | 0
2017- ECONOMIC DEVELOPMENT- Expansion of Bagsakan Center at Guindulman Public Market |  | 500000 |  |  |  | 466560
2018- ECONOMIC DEVELOPMENT- Loan Payment CY 2018 |  | 655642.36 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Construction of FMR, Tabajan to Sawang |  | 1000000 |  |  |  | 895676
2018- ECONOMIC DEVELOPMENT- Construction of FMR at Sitio Albur, Trinidad |  | 195992.95 |  |  |  | 119620
2018- ECONOMIC DEVELOPMENT- Completion of Building & Cottages at Tabunoc Coffee Plantation |  | 200000 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of FMR at Sitio Masayag, Guinacot |  | 36486 |  |  |  | 34835
2018- ECONOMIC DEVELOPMENT- Extention of Public Market particularly at the open space bet. Bagsakan & East Wing bldng. |  | 500000 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT-Rehabilitation of Multi-Purpose Hall at Basdio Marine Sanctuary including construction of 4 units bamboo house w/ CR |  | 61632.8 |  |  |  | 25000
2018- ECONOMIC DEVELOPMENT- Contruction of LGU Pension House (Initial Funding) |  | 1000000 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of FMR at Sitio Poo, Barangay Cat. Sur |  | 130479 |  |  |  | 89120
2018- ECONOMIC DEVELOPMENT- Construction of LGU Pension House (Mun Ordinance No. 2018-04 realignment) |  | 1000000 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of Farm to Market Road in Tuhob, Guio-ang (Mun. Ordinance No. 2018-03 realignment) |  | 32580 |  |  |  | 20000
2018- ECONOMIC DEVELOPMENT- Construction of LGU Pension House |  | 500000 |  |  |  | 372000
2018- ECONOMIC DEVELOPMENT- Concreting of Masayag Farm to Market Road, Guinacot |  | 200000 |  |  |  | 135485
2018- ECONOMIC DEVELOPMENT- Rehabilitation of Irrigation Canal, Guinacot |  | 200000 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of Pathway @ Biabas Barangay Hall |  | 14705.04 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of Pathway @ Purok 5, Barangay Guio-ang |  | 535 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Concreting of Pathway @ Purok 6, Barangay Guio-ang |  | 800 |  |  |  | 0
2018- ECONOMIC DEVELOPMENT- Counterpart for Waterworks Project, Phase II (BUB) |  | 900000 |  |  |  | 857241.86
2018- ECONOMIC DEVELOPMENT- Improvement of Waterworks System- Bulawan |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Payment of Debt |  | 2300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway down to Seashore of Dela Paz, Basdio |  | 100000 |  |  |  | 63540
2019 - ECONOMIC DEVELOPMENT -Rehabilitation of Pathway/Stairs (Riprapping) to Beach, Basdio |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Portion of Prov'l. Road-Central Bato Section (Farm to Market Road) |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Pruta, Bayong (Farm to Market Road) |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Barangay Bayong (Sentro) - (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Purok 5, Biabas (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Sitio Nipot Nipot, Barangay Bulawan |  | 50000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Purok 7, Barangay Bulawan |  | 50000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Fatima, Cabantian (Farm to Market Road) |  | 175000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Pansul, Cabantian (Farm to Market Road) |  | 175000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Camp Bernido, Canhaway (Farm to Market Road) |  | 500000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Sitio Naga, Barangay Cansiwang |  | 50000 |  |  |  | 31970.2
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Barangay Catungawan Norte (Farm to Market Road) |  | 500000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Barangay Catungawan Sur (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Tawid Pasan, Guinacot (Farm to Market Road) |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Saksak, Bato (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Masayag, Barangay Guinacot (Farm to Market Road) |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Sitio Sto. Niño, Barangay Guio-ang (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Labu, Lombog to Barangay Tabunok (Farm to Market Road) |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Mayuga Elem. School |  | 100000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Guinto-owan, Tabunok to Labo, Lombog (from Barangay Tabunok)- (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Albur, Trinidad (Farm to Market Road) |  | 300000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Improvement of Legacy Park & Boulevard at the Rearside of Municipal Building |  | 1000000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Expansion of Public Market Building (Right side of Bagsakan Center) |  | 500000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Municipal Road (Beside Olaguir's Residence) Barangay Sawang |  | 461825.4 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Rehabilitation of Public Market |  | 400000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Rehabilitation of Guindulman Slaughterhouse at Cambanog, Canhaway |  | 500000 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
SUB-TOTAL |  | 18216844.75 |  |  |  | 3382938.06
Environmental Management:
2014- Development of Memorial Cemetery at Guio-ang |  | 752641.55 |  |  |  | 0
2016- Coffee Plantation (Concreting Access Road) |  | 1000000 |  |  |  | 607854
2016- Beautification of the Surrounding of the Mun. Gymnasium Legacy Park |  | 5032 |  |  |  | 0
2017- ENVIRONMENTAL DEVELOPMENT- Construction of River Dike at the Rearside of Brgy Hall, Barangay Casbu |  | 1500000 |  |  |  | 0
2017- ENVIRONMENTAL DEVELOPMENT- Improvement of Municipal Dumpsite, Catungawan Sur |  | 200000 |  |  |  | 0
2017- ENVIRONMENTAL DEVELOPMENT- Completion of Access Road to Municipal Dumpsite, Catungawan Sur |  | 200000 |  |  |  | 0
2017- ENVIRONMENTAL DEVELOPMENT- Initial Develoopment of Municipal Cemetery, Barangay Guio-ang |  | 908075 |  |  |  | 11475
2017- ENVIRONMENTAL DEVELOPMENT- Provision of Concrete Canal Cover, Barangay Drainage System, Sawang |  | 6358.48 |  |  |  | 0
2017- ENVIRONMENTAL DEVELOPMENT- Construction of Drainage Canal at Basdio |  | 50000 |  |  |  | 0
2018- ENVIRONMENTAL DEVELOPMENT- Improvement of Legacy Park at Guindulman to include Landscaping/Greening |  | 500000 |  |  |  | 0
2018- ENVIRONMENTAL DEVELOPMENT- Development/Improvement of LGU Lot in Brgy. Guio-ang (Fill-up Materials) |  | 967388 |  |  |  | 118500
2018- ENVIRONMENTAL DEVELOPMENT- Construction/Rehabilitation of Materials Recovery Facilities (MRF) and closure of dumpsite |  | 513703.31 |  |  |  | 310708.19
2019 - ENVIRONMENTAL DEVELOPMENT - Rehabilitation of Drainage Canal from Jean Felisilda down to DPWH area |  | 250000 |  |  |  | 0
2019 - ENVIRONMENTAL DEVELOPMENT - Improvement of Drainage Canal Along Provincial Highway at Dela Paz near Chapel, Basdio |  | 200000 |  |  |  | 0
2019 - ENVIRONMENTAL DEVELOPMENT - Construction of Stairs to Building/Cottages of Coffee Plantation at Barangay Tabunok |  | 500000 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
|  | 0 |  |  |  | 0
SUB-TOTAL |  | 7553198.34 |  |  |  | 1048537.19
GRAND TOTALS |  | 40266888.41 |  |  |  | 7461949.84
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD) AIDA L. MAHILUM |  |  |  |  | (SGD) MARIA FE A. PIEZAS, M.D.
Municipal Budget Officer | [5 empty] | Local Chief Evecutive