## Form 7
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE THIRD QUARTER, CY 2020
Province, City or Municipality: GUINDULMAN, BOHOL
Program or Project | Location | Total Cost (Balance Beg. 1/1/2019) | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development:
2016- SOCIAL DEVELOPMENT- Counterpart to KALAHI-NCDDP Project (part of 1,739,070.00) |  | 284099.57 |  |  |  | 284099.57
2016- COVID-RELATED: Expenses for consultation/rental/lease of space or building to accommodate COVID-19 patients and persons under monitoring/investigation |  | 200000 |  |  |  | 200000
2017- SOCIAL DEVELOPMENT- Counterpart to KALAHI-NCDDP Project (part of 1,739,070.00) |  | 1158150 |  |  |  | 1158150
2017- COVID-RELATED: Expenses for consultation/rental/lease of space or building to accommodate COVID-19 patients and persons under monitoring/investigation |  | 1550000 |  |  |  | 447590.89
2018- SOCIAL DEVELOPMENT- Construction of Mayuga- Footbridge and Pathway from Chapel to Sitio Camagong I |  | 100000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Construction of Mayuga- Footbridge and Pathway from Sitio Camagong II to Chapel |  | 100000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Biabas- Initial Construction of Senior Citizens' Building |  | 150000 |  |  |  | 0
2018- SOCIAL DEVELOPMENT- Mayuga- Improvement/Upgrading of Mayuga Health Center (part of 1,000,000.00) |  | 605279.88 |  |  |  | 264080.5
2018- SOCIAL DEVELOPMENT- Counterpart to KALAHI-NCDDP Project (part of 1,739,070.00) |  | 296820.43 |  |  |  | 296820.43
2018- SOCIAL DEVELOPMENT- Construction of Multi-Purpose Hall at LGU Lot in Guio-ang |  | 1488383.71 |  |  |  | 0
2018- COVID-RELATED: Expenses for consultation/rental/lease of space or building to accommodate COVID-19 patients and persons under monitoring/investigation |  | 22111 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT - Completion of Tribal House (Eskaya Tribe) at Barangay Biabas |  | 97117.5 |  |  |  | 97117.5
2019 - SOCIAL DEVELOPMENT -Constructon of School Stage at Barangay Casbu |  | 181090 |  |  |  | 181090
2019 - SOCIAL DEVELOPMENT -Improvement of Tubod Spring at Barangay Guio-ang |  | 300000 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Improvement of Mayuga Waterworks System, Barangay Mayuga |  | 300000 |  |  |  | 297180
2019 - SOCIAL DEVELOPMENT -Installation of Street Lightings along FCB, Bonita & Liao Street, Barangay Sawang |  | 235973 |  |  |  | 235973
2019 - SOCIAL DEVELOPMENT -Additional Funding for the Completion of Covered Court at Barangay Trinidad |  | 180000 |  |  |  | 180000
2019 - SOCIAL DEVELOPMENT -Site Development of LGU Lot in Guio-ang |  | 208550 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Mayuga- Improvement/Upgrading of Mayuga Health Center (part of 1,000,000.00) |  | 394720.12 |  |  |  | 0
2019 - SOCIAL DEVELOPMENT -Catungawan Sur Waterworks Project |  | 473217.29 |  |  |  | 473217.29
2019- SOCIAL DEVELOPMENT: Bato- Construction/Rehabilitation of Waterworks System |  | 500000 |  |  |  | 395660.55
2019- SOCIAL DEVELOPMENT: Tabajan- Improvement of Multi-Purpose Covered Court |  | 229159 |  |  |  | 229109
2019- SOCIAL DEVELOPMENT: Guio-ang- Initial Construction of Multi-Purpose Building (Senior Citizen) |  | 99990 |  |  |  | 99990
2019- COVID-RELATED: Expenses for consultation/rental/lease of space or building to accommodate COVID-19 patients and persons under monitoring/investigation |  | 227889 |  |  |  | 0
2019- COVID-RELATED: Expenses for food and transportation (including fuel) and accomodation of medical and LGU personnel directly involved in the implementation of COVID-19 PPAs |  | 1000000 |  |  |  | 1000000
2019-COVID-RELATED: Expenses for other necessary COVID-19 related PPAs |  | 1368584.22 |  |  |  | 1006507.84
2020- SOCIAL DEVELOPMENT: Basdio- Construction Reservoir at Sitio dela Paz |  | 200000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Basdio- Procurement/Installation of Water Pump/Pipe at Zone 1 |  | 75000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Basdio- Improvement of Fence at Basdio Elementary School (school also used as Evacuation Center) |  | 175000 |  |  |  | 99820
2020- SOCIAL DEVELOPMENT: Bato- Waterworks System @ Sitio Lower Mahanay |  | 200000 |  |  |  | 175941.3
2020- SOCIAL DEVELOPMENT: Bato- Waterworks System @ Sitio Saksak |  | 200000 |  |  |  | 99121.44
2020- SOCIAL DEVELOPMENT: Bato- Improvement of Central Bato Multi-Purpose Hall/Stage |  | 100000 |  |  |  | 70870
2020- SOCIAL DEVELOPMENT: Bayong- Waterworks Canloy-a |  | 500000 |  |  |  | 410713.5
2020- SOCIAL DEVELOPMENT: Biabas- Waterworks System |  | 500000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Bulawan- Improvement of Health Center |  | 100000 |  |  |  | 83620
2020- SOCIAL DEVELOPMENT: Cabantian- Waterworks System for Puroks 1, 4, 5, 6, 7 of Brgy Cabantian |  | 500000 |  |  |  | 66995
2020- SOCIAL DEVELOPMENT: Cansiwang- Completion of Multi-Purpose Hall |  | 100000 |  |  |  | 99916
2020- SOCIAL DEVELOPMENT: Cansiwang- Waterworks Project (covering all Sitios) |  | 400000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Casbu- Construction of Streetlight going to Evacuation Center |  | 200000 |  |  |  | 125486
2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Health Center |  | 200000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Waterworks (covering all Sitios) |  | 200000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Perimeter Fence @ Cabugan E/S (school also used as Evacuation Center) |  | 100000 |  |  |  | 69065
2020- SOCIAL DEVELOPMENT: Guinacot- Waterworks System |  | 500000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Guio-ang- Waterworks System |  | 500000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Lombog- Purchase of Watermeter 200 units |  | 300000 |  |  |  | 259000
2020- SOCIAL DEVELOPMENT: Sawang- Completion of Multi-Purpose Covered Court |  | 500000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Tabajan- Construction of Multi-Purpose Hall/Stage |  | 500000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Tabunok- Waterworks Purok 1,2,3,4 |  | 500000 |  |  |  | 228064.55
2020- SOCIAL DEVELOPMENT: Trinidad- Construction/Improvement of Evacuation Center |  | 400000 |  |  |  | 0
2020- SOCIAL DEVELOPMENT: Trinidad- Solar Streetlighting (Sitio Albur, Trinidad) |  | 100000 |  |  |  | 77740
2020- SOCIAL DEVELOPMENT: Major Repair of the Training Center/Municipal Hall & Comfort Rooms within the Municipal Hall |  | 950000 |  |  |  | 813036
2020-COVID-RELATED: Procurement of Thermal Scanner |  | 122500 |  |  |  | 122500
2020-COVID-RELATED: Construction of Quarantine Facility |  | 1000000 |  |  |  | 299764.9
2020-COVID-RELATED: Construction of Isolation Facility |  | 1000000 |  |  |  | 0
2020-COVID-RELATED: Expenses for necessary COVID-19 related PPAs & expenses |  | 3327500 |  |  |  | 414854.8
2020-COVID-RELATED: Procurement of disinfectants, sprayers, disinfection tents and other disinfecting supplies and misting equipment |  | 200000 |  |  |  | 0
2020-COVID-RELATED: Procurement of other equipment, reagents and kits for COVID-19 testing |  | 200000 |  |  |  | 0
2020-COVID-RELATED: Purchase of PPEs/gears |  | 300000 |  |  |  | 232325
SUB-TOTAL |  | 25901134.72 |  |  |  | 10595420.06
Economic Development:
2017- ECONOMIC DEVELOPMENT- Improvement of Waterworks, Barangay Tabunoc |  | 200000 |  |  |  | 194602
2018- ECONOMIC DEVELOPMENT- Rehabilitation of Irrigation Canal, Guinacot |  | 200000 |  |  |  | 0
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Camp Bernido, Canhaway (Farm to Market Road) |  | 230730 |  |  |  | 120775
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Barangay Catungawan Norte (Farm to Market Road) |  | 230730 |  |  |  | 120775
2019 - ECONOMIC DEVELOPMENT -Concreting of Barangay Road at Sitio Tawid Pasan, Guinacot (Farm to Market Road) |  | 200000 |  |  |  | 171205
2019 - ECONOMIC DEVELOPMENT -Concreting of Pathway at Mayuga Elem. School |  | 30050 |  |  |  | 30050
2019 - ECONOMIC DEVELOPMENT -Rehabilitation of Public Market |  | 400000 |  |  |  | 92608
2019- ECONOMIC DEVELOPMENT: Rehabilitation of Public Market |  | 567105.28 |  |  |  | 399995
2019- ECONOMIC DEVELOPMENT: Rehabilitation of Gymnasium |  | 400000 |  |  |  | 76365
2020- ECONOMIC DEVELOPMENT: Bulawan- Solar Energy Panel Installation for Submersible Water Pump |  | 400000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Casbu- Solar Energy for Water Pump |  | 300000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Canhaway- Farm to Market Road Sitio Bunhayag Bugang |  | 500000 |  |  |  | 360195
2020- ECONOMIC DEVELOPMENT: Catungawan Sur- Farm to Market Road |  | 500000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Lombog- Farm to Market Road Sitio Ilaya 2 |  | 200000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Mayuga- Reopening of Farm to Market Road at Sitio Lungon |  | 500000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Major Repair of Windows and Repainting of Gymnasium |  | 1000000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Rehabilitation of Public Market |  | 1000000 |  |  |  | 0
2020- ECONOMIC DEVELOPMENT: Payment of Loan |  | 3510344.4 |  |  |  | 646914.4
SUB-TOTAL |  | 10368959.68 |  |  |  | 2213484.4
Environmental Management:
2014 & 2016- Waste Water Treatment Plant (part of 3,100,000.00) |  | 376339.75 |  |  |  | 376339.75
2017- Waste Water Treatment Plant (part of 3,100,000.00) |  | 664973.28 |  |  |  | 664973.28
2018- ENVIRONMENTAL DEVELOPMENT- Development/Improvement of LGU Lot in Brgy. Guio-ang (Fill-up Materials) |  | 779738 |  |  |  | 0
2018- ENVIRONMENTAL DEVELOPMENT- Construction/Rehabilitation of Materials Recovery Facilities (MRF) and closure of dumpsite |  | 112515.83 |  |  |  | 112515.83
2018- Waste Water Treatment Plant (part of 3,100,000.00) |  | 1601186.97 |  |  |  | 1551186.97
2019 - ENVIRONMENTAL DEVELOPMENT - Improvement of Drainage Canal Along Provincial Highway at Dela Paz near Chapel, Basdio |  | 169242.5 |  |  |  | 169242.5
2019- ENVIRONMENTAL DEVELOPMENT: Construction/ Rehabilitation of Material Recovery Facility (MRF) & Closure of Dumpsite |  | 388284.17 |  |  |  | 388284.17
2020- ENVIRONMENTAL DEVELOPMENT: Purchase of Garbage Compactor |  | 2000000 |  |  |  | 1999000
SUB-TOTAL |  | 6092280.5 |  |  |  | 5261542.5
GRAND TOTALS |  | 42362374.9 |  |  |  | 18070446.96
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
AIDA L. MAHILUM | [5 empty] | MARIA FE A. PIEZAS, M.D.
Municipal Budget Officer | [5 empty] | LCE

## Sheet1
Capital Outlays:
CY 2020: 20% of IRA for Local Development Fund
A. Social Development:
|  | Basdio- Construction Reservoir at Sitio dela Paz | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Basdio- Construction Reservoir at Sitio dela Paz
|  | Basdio- Construction of Bonbon Beach Catch Basin | [6 empty] | 50000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Basdio- Construction of Bonbon Beach Catch Basin
|  | Basdio- Procurement/Installation of Water Pump/Pipe at Zone 1 | [6 empty] | 75000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Basdio- Procurement/Installation of Water Pump/Pipe at Zone 1
|  | Basdio- Improvement of Fence at Basdio Elementary School (school also used as Evacuation Center) | [6 empty] | 175000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Basdio- Improvement of Fence at Basdio Elementary School (school also used as Evacuation Center)
|  | Bato- Waterworks System @ Sitio Lower Mahanay | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Bato- Waterworks System @ Sitio Lower Mahanay
|  | Bato- Waterworks System @ Sitio Saksak | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Bato- Waterworks System @ Sitio Saksak
|  | Bato- Improvement of Central Bato Multi-Purpose Hall/Stage | [6 empty] | 100000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Bato- Improvement of Central Bato Multi-Purpose Hall/Stage
|  | Bayong- Waterworks Canloy-a | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Bayong- Waterworks Canloy-a
|  | Biabas- Waterworks System | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Biabas- Waterworks System
|  | Bulawan- Improvement of Health Center | [6 empty] | 100000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Bulawan- Improvement of Health Center
|  | Cabantian- Waterworks System for Puroks 1, 4, 5, 6, 7 of Brgy Cabantian | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Cabantian- Waterworks System for Puroks 1, 4, 5, 6, 7 of Brgy Cabantian
|  | Cansiwang- Completion of Multi-Purpose Hall | [6 empty] | 100000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Cansiwang- Completion of Multi-Purpose Hall
|  | Cansiwang- Waterworks Project (covering all Sitios) | [6 empty] | 400000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Cansiwang- Waterworks Project (covering all Sitios)
|  | Casbu- Construction of Streetlight going to Evacuation Center | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Casbu- Construction of Streetlight going to Evacuation Center
|  | Catungawan Norte- Improvement of Health Center | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Health Center
|  | Catungawan Norte- Improvement of Waterworks (covering all Sitios) | [6 empty] | 200000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Waterworks (covering all Sitios)
|  | Catungawan Norte- Improvement of Perimeter Fence @ Cabugan E/S (school also used as Evacuation Center) | [6 empty] | 100000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Catungawan Norte- Improvement of Perimeter Fence @ Cabugan E/S (school also used as Evacuation Center)
|  | Guinacot- Waterworks System | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Guinacot- Waterworks System
|  | Guio-ang- Waterworks System | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Guio-ang- Waterworks System
|  | Lombog- Purchase of Watermeter 200 units | [6 empty] | 300000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Lombog- Purchase of Watermeter 200 units
|  | Sawang- Completion of Multi-Purpose Covered Court | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Sawang- Completion of Multi-Purpose Covered Court
|  | Tabajan- Construction of Multi-Purpose Hall/Stage | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Tabajan- Construction of Multi-Purpose Hall/Stage
|  | Tabunok- Waterworks Purok 1,2,3,4 | [6 empty] | 500000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Tabunok- Waterworks Purok 1,2,3,4
|  | Trinidad- Construction/Improvement of Evacuation Center | [6 empty] | 400000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Trinidad- Construction/Improvement of Evacuation Center
|  | Trinidad- Solar Streetlighting (Sitio Albur, Trinidad) | [6 empty] | 100000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Trinidad- Solar Streetlighting (Sitio Albur, Trinidad)
|  | Major Repair of the Training Center/Municipal Hall & Comfort Rooms within the Municipal Hall | [6 empty] | 950000 | 2020- SOCIAL DEVELOPMENT: | 2020- SOCIAL DEVELOPMENT: Major Repair of the Training Center/Municipal Hall & Comfort Rooms within the Municipal Hall
|  |  | Sub-Total, Social Development |  | 0 | 0 | 0 | 0 | 8050000
B. Economic Development:
|  | Bulawan- Solar Energy Panel Installation for Submersible Water Pump | [6 empty] | 400000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Bulawan- Solar Energy Panel Installation for Submersible Water Pump
|  | Casbu- Solar Energy for Water Pump | [6 empty] | 300000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Casbu- Solar Energy for Water Pump
|  | Canhaway- Farm to Market Road Sitio Bunhayag Bugang | [6 empty] | 500000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Canhaway- Farm to Market Road Sitio Bunhayag Bugang
|  | Catungawan Sur- Farm to Market Road | [6 empty] | 500000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Catungawan Sur- Farm to Market Road
|  | Lombog- Farm to Market Road Sitio Ilaya 2 | [6 empty] | 200000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Lombog- Farm to Market Road Sitio Ilaya 2
|  | Mayuga- Reopening of Farm to Market Road at Sitio Lungon | [6 empty] | 500000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Mayuga- Reopening of Farm to Market Road at Sitio Lungon
|  | Major Repair of Windows and Repainting of Gymnasium | [6 empty] | 1000000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Major Repair of Windows and Repainting of Gymnasium
|  | Rehabilitation of Public Market | [6 empty] | 1000000 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Rehabilitation of Public Market
|  | Payment of Loan | [6 empty] | 3510344.4 | 2020- ECONOMIC DEVELOPMENT: | 2020- ECONOMIC DEVELOPMENT: Payment of Loan
|  |  | Sub-Total, Economic Development |  | 0 | 0 | 0 | 0 | 7910344.4
C. Environmental Development:
|  | Purchase of Garbage Compactor | [6 empty] | 2000000 | 2020- ENVIRONMENTAL DEVELOPMENT: | 2020- ENVIRONMENTAL DEVELOPMENT: Purchase of Garbage Compactor
|  | Installation of Solar Panel for Municipal Hall, Gymnasium and Market | [6 empty] | 6100000 | 2020- ENVIRONMENTAL DEVELOPMENT: | 2020- ENVIRONMENTAL DEVELOPMENT: Installation of Solar Panel for Municipal Hall, Gymnasium and Market
|  |  | Sub-Total, Environmental Development |  | 0 | 0 | 0 | 0 | 8100000
CY 2019: 20% of IRA for Local Development Fund | [5 empty] | 1542582.2 | 19819243.2 | 21361825.4
CY 2018: 20% of IRA for Local Development Fund |  |  |  |  | 20950878.54
|  |  | GRAND TOTAL, 20% LDF |  | 20950878.54 | 1542582.2 | 19819243.2 | 21361825.4 | 24060344.4 | 18272180.5
-2000000
Prepared: |  |  |  | Reviewed: |  |  |  | Approved: |  | 42332524.9
MUNICIPAL DEVELOPMENT COUNCIL: |  |  |  | AIDA L. MAHILUM |  |  |  | MARIA FE A. PIEZAS, M.D.
By: |  |  |  | Municipal Budget Officer |  |  |  | Local Chief Executive
EnP. RUBEN D. BOYBANTING